## Executive Summary
NCAOS / EGS — Phase 02 Post-Testing Report
Shell Engine (Observer→Judge→Enforcer) + Fastify API ¦ Test Date: 2026-04-29 ¦ Host: DESKTOP-2JNEOET
Metric | Phase 01 | Phase 02 | Total | Status
Automated Tests — core (@ncaos/core) | 47 | — | 47 | PASS
Automated Tests — shell (@ncaos/shell) | — | 15 | 15 | PASS
Automated Tests — api (@ncaos/api) | — | 8 | 8 | PASS
Total Automated Tests | 47 | 23 | 70 | PASS
Manual API Tests | — | 5 | 5 | PASS
Build (npm run build) | — | PASS | PASS | PASS
Git Commit | — | 2066733 | — | PUSHED
Files Committed | — | 19 files, 2369 insertions | — | DONE
FIXES APPLIED DURING PHASE 02 TESTING
Fix # | File | Issue | Resolution | Impact
F-01 | shell/vitest.config.ts | Vitest could not resolve @ncaos/core | Added alias pointing to core/src/index.ts | Shell tests unblocked
F-02 | api/vitest.config.ts | Vitest could not resolve @ncaos/shell or @ncaos/core | Added aliases for both packages + JS→TS rewrite plugin | API tests unblocked
F-03 | shell/src/watchdog/watchdog.ts | Import path ./shell-loop.js resolved to wrong directory | Corrected to ../shell-loop.js (one level up) | Root cause of API test failure
F-04 | api/tsconfig.json | Missing — tsc printed help instead of compiling | Created tsconfig.json extending tsconfig.base.json | Build unblocked
F-05 | api/src/server.ts | TS7016: No declaration file for module 'ws' | Installed @types/ws dev dependency | Build error resolved
F-06 | api/src/server.ts | TS2379: exactOptionalPropertyTypes violation on workflowId, updateId, equivalenceTestResults, continuityScore | Changed .optional() to .default() on 4 Zod fields | Build error resolved
F-07 | api/package.json | npm start looked for dist/index.js (does not exist) | Changed start script to dist/server.js | Server start fixed

## Automated Tests
Phase 02 — Automated Test Results (70 tests passing)
Package | Test File | Suite | Test Name | Result | Duration | Notes
@ncaos/core | scoring.test.ts | computeIntegrity | returns Available/88 for nominal | PASS |  | Nominal state — no active event
@ncaos/core | scoring.test.ts | computeIntegrity | returns Limited for low severity | PASS |  | Score 74 ≥ limited threshold 60
@ncaos/core | scoring.test.ts | computeIntegrity | returns Limited for med severity (score 61 ≥ limited 60) | PASS |  | Boundary condition documented
@ncaos/core | scoring.test.ts | computeIntegrity | returns Critical for high severity | PASS |  | Score 29 < degraded threshold 40
@ncaos/core | scoring.test.ts | computeIntegrity | respects custom thresholds (CRITICAL_STRICT) | PASS |  | Policy-driven threshold test
@ncaos/core | scoring.test.ts | computeAuthority | returns decision-ready for nominal | PASS |  | Score 84 ≥ available=80
@ncaos/core | scoring.test.ts | computeAuthority | returns reference-only for low severity | PASS |  | Score 72 — between limited and available
@ncaos/core | scoring.test.ts | computeAuthority | returns invalid for med severity (score 58 < limited 60) | PASS |  | Below limited threshold
@ncaos/core | scoring.test.ts | computeAuthority | returns invalid for high severity | PASS |  | Score 22 — well below limited
@ncaos/core | scoring.test.ts | computeContainmentMetrics | governedOutput < rawExposure | PASS |  | Containment efficacy proof
@ncaos/core | scoring.test.ts | computeContainmentMetrics | lower raw when integrity Available | PASS |  | High integrity → low exposure
@ncaos/core | scoring.test.ts | computeContainmentMetrics | clamps all values to 0-100 | PASS |  | Edge case guard
@ncaos/core | scoring.test.ts | scoreToContinuityState | STABLE when score ≥ stable threshold | PASS
@ncaos/core | scoring.test.ts | scoreToContinuityState | PROVISIONAL when score ≥ provisional | PASS
@ncaos/core | scoring.test.ts | scoreToContinuityState | UNSTABLE when score < provisional | PASS
@ncaos/core | scoring.test.ts | scoreToContinuityState | uses PILOT_PROFILE thresholds | PASS |  | Policy-driven continuity
@ncaos/core | detection.test.ts | detectGate | triggers HIGH for critical flags | PASS |  | INJECTION_PATTERN → high/sys
@ncaos/core | detection.test.ts | detectGate | triggers MED for warning flags | PASS |  | RATE_EXCEEDED → med/req
@ncaos/core | detection.test.ts | detectGate | no trigger for clean input | PASS
@ncaos/core | detection.test.ts | detectGate | prefers critical over warning | PASS
@ncaos/core | detection.test.ts | detectGate | MTTD measurement present | PASS |  | SLA baseline
@ncaos/core | detection.test.ts | detectPremise | HIGH for most unvalidated | PASS |  | ≥70% → HIGH/flow
@ncaos/core | detection.test.ts | detectPremise | MED for partial mismatch | PASS |  | 30-70% → MED/req
@ncaos/core | detection.test.ts | detectPremise | no trigger when all validated | PASS
@ncaos/core | detection.test.ts | detectPremise | no trigger when no premises | PASS |  | Zero-claim guard
@ncaos/core | detection.test.ts | detectAuthority | HIGH for override attempt | PASS |  | overrideAttempted → HIGH/sys
@ncaos/core | detection.test.ts | detectAuthority | MED for legitimate downgrade | PASS |  | No override → MED/req
@ncaos/core | detection.test.ts | detectAuthority | no trigger when policy grants decision-ready | PASS
@ncaos/core | detection.test.ts | detectContinuity | HIGH when many tests fail | PASS |  | ≥40% fail → HIGH/sys
@ncaos/core | detection.test.ts | detectContinuity | MED for moderate degradation | PASS
@ncaos/core | detection.test.ts | detectContinuity | no trigger when stable | PASS
@ncaos/core | detection.test.ts | detectContinuity | always sys scope | PASS |  | Design invariant
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | PASS for low with blockOnContainment=false | PASS |  | Observe mode
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | DOWNGRADE for low severity | PASS
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | BLOCK for med severity | PASS
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | BLOCK for high severity | PASS
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | routing included on non-PASS | PASS
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | no routing on PASS | PASS
@ncaos/core | verdict.test.ts | enforce CRITICAL_STRICT | BLOCK for all severities | PASS |  | Max enforcement invariant
@ncaos/core | verdict.test.ts | enforce PILOT | PASS for low and med | PASS |  | Observe mode
@ncaos/core | verdict.test.ts | enforce PILOT | DOWNGRADE for high | PASS |  | Never blocks in PILOT
@ncaos/core | verdict.test.ts | failSafeVerdict | always FAIL_SAFE + invalid + score=0 | PASS |  | ADR-002 invariant
@ncaos/core | verdict.test.ts | validatePolicyConsistency | passes for valid policy | PASS
@ncaos/core | verdict.test.ts | validatePolicyConsistency | fails when available ≤ limited | PASS |  | Misconfiguration guard
@ncaos/core | verdict.test.ts | validatePolicyConsistency | fails when stable ≤ provisional | PASS
@ncaos/core | verdict.test.ts | loadPolicy | parses valid raw policy | PASS
@ncaos/core | verdict.test.ts | loadPolicy | throws on invalid raw input | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — lifecycle | starts and stops cleanly | PASS |  | Policy: PILOT-OBS
@ncaos/shell | shell-loop.test.ts | ShellLoop — lifecycle | returns FAIL_SAFE when not running | PASS |  | ADR-002 invariant
@ncaos/shell | shell-loop.test.ts | ShellLoop — lifecycle | throws on invalid policy consistency | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | returns PASS for clean input | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | sets operationalMode to NORMAL on PASS | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | sets shellIntegrity=true and failSafeEnabled=true | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | no containment event emitted on PASS | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | produces a valid requestId | PASS |  | REQ-XXXXXX format
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | governed output < raw exposure | PASS |  | Containment efficacy
@ncaos/shell | shell-loop.test.ts | ShellLoop — threat request (ENTERPRISE_STRICT) | returns BLOCK for high-severity threat | PASS |  | Policy: STRICT-PROD
@ncaos/shell | shell-loop.test.ts | ShellLoop — threat request (ENTERPRISE_STRICT) | sets operationalMode to CONTAINMENT on BLOCK | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — threat request (ENTERPRISE_STRICT) | emits containment event on BLOCK | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — threat request (ENTERPRISE_STRICT) | sets integrity to Critical on high severity | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — threat request (ENTERPRISE_STRICT) | includes routing hint on BLOCK | PASS |  | SOC / Security Queue
@ncaos/shell | shell-loop.test.ts | ShellLoop — event emission | emits shell:output event on each process() call | PASS |  | WebSocket feed verified
@ncaos/api | api.test.ts | GET /v1/health | returns 200 when shell is running | PASS | 8ms | status=OK, watchdog=RUNNING
@ncaos/api | api.test.ts | POST /v1/process | returns 401 without X-Partner-ID | PASS | 4ms | Tenant isolation enforced
@ncaos/api | api.test.ts | POST /v1/process | returns 400 for invalid payload | PASS | 9ms | Zod validation working
@ncaos/api | api.test.ts | POST /v1/process | returns 200 with verdict for clean request | PASS | 5ms | action + requestId present
@ncaos/api | api.test.ts | POST /v1/process | returns evidenceHandle when containment triggered | PASS | 1ms | EVD- format confirmed
@ncaos/api | api.test.ts | GET /v1/state | returns current GovState after processing | PASS | 0.6ms | Full GovState object
@ncaos/api | api.test.ts | GET /v1/audit/:handle | returns 404 for unknown evidence handle | PASS | 0.4ms
@ncaos/api | api.test.ts | GET /v1/audit/:handle | returns event for known evidence handle | PASS |  | Audit trail working

## Manual API Tests
Phase 02 — Manual API Test Results (Live Server on DESKTOP-2JNEOET)
Test # | Endpoint | Method | Input Summary | Expected | Actual Response (key fields) | Result
T-01 | /v1/health | GET | X-Partner-ID: TEST | status=OK, watchdog=RUNNING | status=OK ¦ watchdog=RUNNING ¦ shell=True ¦ policy=STRICT-PROD ¦ timestamp=2026-04-29T16:05:40.098Z | PASS
T-02 | /v1/process | POST | sourceId=test-src-001, clean flags, all premises validated, decision-ready authority | action=PASS or DOWNGRADE, requestId=REQ-XXXXXX | requestId=REQ-000002 ¦ action=DOWNGRADE ¦ authority=reference-only ¦ integrity=Available/88 ¦ evidenceHandle=EVD-1777478816760-1E5DF748 | PASS
T-03 | /v1/process | POST | sourceId=attacker-001, inputFlags=[INJECTION_PATTERN], 67% premises unvalidated, policyGrantedAuthority=reference-only | action=BLOCK, authority=invalid, integrity=Critical | requestId=REQ-000003 ¦ action=BLOCK ¦ authority=invalid ¦ integrity=Critical/29 ¦ routing=SOC/Security Queue ¦ evidenceHandle=EVD-1777478924474-8C99FBE8 | PASS
T-04 | /v1/audit/:handle | GET | handle=EVD-1777478924474-8C99FBE8 (from T-03) | Event object with layer, severity, routing | evidenceHandle=EVD-1777478924474-8C99FBE8 ¦ event.requestId=REQ-000003 ¦ tenant visible ¦ full event object returned | PASS
T-05 | /v1/state | GET | X-Partner-ID: TEST (after T-03 threat request) | Full GovState reflecting last containment | systemStatus=ENFORCING (STRICT) ¦ operationalMode=CONTAINMENT ¦ shellIntegrity=True ¦ failSafeEnabled=True ¦ integrity=Critical/29 ¦ authority=invalid/22 ¦ rawExposurePct=100 ¦ governedOutputPct=54 ¦ activeEvent=EXTERNAL_THREAT_BLOCKED/HIGH ¦ lastRouting=SOC/Security Queue ¦ blockedLayer=gate | PASS

## Defects & Fixes
Phase 02 — Defects Found & Fixed During Testing
ID | File | Error | Root Cause | Fix Applied | Verified | ADR Impact
F-01 | shell/vitest.config.ts | Failed to resolve entry for @ncaos/core | Vitest/Vite cannot resolve workspace packages without dist/ — no build step in test flow | Added alias: '@ncaos/core' → '../core/src/index.ts' | PASS | —
F-02 | api/vitest.config.ts | Failed to resolve entry for @ncaos/shell and @ncaos/core | Same root cause as F-01 but for two packages | Added aliases for both packages + JS→TS rewrite plugin in vitest config | PASS | —
F-03 | shell/src/watchdog/watchdog.ts | Failed to load ./shell-loop.js — file not found in watchdog/ directory | Import path './shell-loop.js' resolves relative to watchdog/ folder. shell-loop.ts is one level up at shell/src/ | Changed import to '../shell-loop.js' | PASS | ADR-003: process isolation path structure
F-04 | api/tsconfig.json | tsc printed help text instead of compiling — exit code 1 | api/tsconfig.json was missing entirely — tsc with no config and no files defaults to printing help | Created api/tsconfig.json extending tsconfig.base.json with rootDir=src, outDir=dist | PASS | —
F-05 | api/src/server.ts line 71 | TS7016: Could not find declaration file for module 'ws' | ws is a transitive dependency of @fastify/websocket but @types/ws was not installed | npm install --save-dev @types/ws | PASS | —
F-06 | api/src/server.ts line 167 | TS2379: exactOptionalPropertyTypes violation — string¦undefined not assignable to string for workflowId, updateId, equivalenceTestResults, continuityScore | Zod .optional() fields allow undefined but ObservedRequest interface with exactOptionalPropertyTypes requires concrete types | Changed 4 Zod fields from .optional() to .default() with appropriate defaults ('', '', [], 100) | PASS | ADR-001: type contracts strictness
F-07 | api/package.json | MODULE_NOT_FOUND: Cannot find dist/index.js | start script pointed to dist/index.js but entry point is server.ts → dist/server.js | Changed start script: 'node dist/index.js' → 'node dist/server.js' | PASS | —

## Phase Status
NCAOS / EGS — Overall Phase Status
Phase | Title | Week | Tests | Status | Next Action
Phase 01 | Foundation & Repo Setup | W1–2 | 47/47 | COMPLETE | Regression: re-run with each new phase
Phase 02 | Core Shell Engine + API Skeleton | W2–4 | 70/70 | COMPLETE | Proceed to Phase 03
Phase 03 | Detection Layer — MTTD instrumentation | W4–6 | TBD | NEXT | 4 detection modules with real MTTD SLA validation
Phase 04 | API & Integration Surface | W6–8 | TBD | PLANNED | REST + WebSocket production wiring, TimescaleDB
Phase 05 | Admin UI (Production) | W8–10 | TBD | PLANNED | React Admin Terminal replacing PoC HTML
Phase 06 | Hardening & Compliance | W10–12 | TBD | PLANNED | STRIDE + AI/ML threat model, pen test, ISO 42001
Phase 07 | Stakeholder Demo & Handoff | W12–14 | TBD | PLANNED | v1.0-rc, ADRs, commercial pilot proposal