## Executive Summary
NCAOS / EGS — Phase 04 Post-Testing Report
API Integration Surface · Per-Tenant Isolation · Sequence Interface (Toru-William) ¦ Test Date: 2026-05-07 ¦ Host: SGWLWH000683
Package | Phase | Test Files | Tests | Fixes | Status | Version
@ncaos/core | Phase 01 | 3 | 47 | 2 test expectation fixes | PASS | v0.1.0
@ncaos/shell | Phase 02 | 1 | 15 | 3 config/path fixes | PASS | v0.2.0
@ncaos/api | Phase 02→04 | 4 | 65 | 7 Phase 04 fixes | PASS | v0.4.0
@ncaos/detection | Phase 03 | 3 | 54 | 3 test alignment fixes | PASS | v0.3.0
CUMULATIVE TOTAL | 01–04 | 11 | 181 | — | ALL PASS | v0.4.0
PHASE 04 — NEW MODULES & ROUTES
File | Module | Key Capability | Tests | Phase | Status | ADR
api/src/store/event-store.ts | EventStore | Append-only log, cursor-based pagination, layer/severity/action filters, sequenceId linking, summarizeSequence() behavioral pattern analysis | 23 | 04 | PASS | —
api/src/store/policy-store.ts | PolicyStore | Per-tenant active policy, Zod + consistency validation, change history (last 10), policy:changed event emission | 7 | 04 | PASS | —
api/src/detectors/tenant-registry.ts | TenantDetectorRegistry | One GateDetector, PremiseDetector, AuthorityDetector, ContinuityDetector, DetectionRegistry per PARTNER_ID | 8 | 04 | PASS | ADR-005
api/src/server.ts (upgraded) | Fastify Server | 14 routes total — 9 new/upgraded Phase 04 routes including sequence interface | 18 | 04 | PASS | —
FIXES APPLIED DURING PHASE 04 TESTING
Fix # | File | Issue | Root Cause | Fix Applied | Verified
F-01 | api/vitest.config.ts | 14 api-v4.test.ts tests failed — routes not found | vitest config missing @ncaos/detection alias. TenantDetectorRegistry imports from detection package which Vite couldn't resolve. | Added '@ncaos/detection' alias pointing to detection/src/index.ts | PASS
F-02 | shell/src/judge/judge.ts | Sequence endpoints returned empty — activeSequences: 0 | workflowId carried into detectPremise() but not declared in JudgmentResult interface and not included in return object. | Added workflowId?: string to JudgmentResult. Added workflowId: req.workflowId ¦¦ undefined to judge() return. | PASS
F-03 | shell/src/enforcer/enforcer.ts | sequenceId never populated in EventStore | Even with judge.ts fixed, workflowId wasn't passed to GovEvent. EventStore derives sequenceId from GovEvent.workflowId. | Added workflowId: j.workflowId to _buildGovEvent() return object. | PASS
F-04 | egs/package.json | npm install failed — JSONParseError at position 220 | Missing comma after 'ui' when adding 'detection' to workspaces array. | Added missing comma: '"ui",' before '"detection"' | PASS
F-05 | api/src/server.ts (build) | npm run build failed — @types/ws missing | ws is a transitive dep of @fastify/websocket but @types/ws was not installed. | npm install --save-dev @types/ws | PASS
F-06 | api/src/server.ts | TS2379 exactOptionalPropertyTypes violations | 4 Zod .optional() fields incompatible with ObservedRequest interface strict types. | Changed workflowId, updateId, equivalenceTestResults, continuityScore from .optional() to .default() | PASS
F-07 | api/package.json | npm start: Cannot find dist/index.js | start script pointed to dist/index.js but entry point compiles to dist/server.js | Changed start script: node dist/index.js → node dist/server.js | PASS

## Automated Tests (181)
Phase 04 — Full Automated Test Suite (181 tests passing across 4 packages)
Package | Test File | Suite | Test Name | Result | Notes
@ncaos/core | detection.test.ts | detectGate | triggers HIGH for critical flags | PASS | INJECTION_PATTERN → high/sys
@ncaos/core | detection.test.ts | detectGate | triggers MED for warning flags | PASS | RATE_EXCEEDED → med/req
@ncaos/core | detection.test.ts | detectGate | no trigger for clean input | PASS
@ncaos/core | detection.test.ts | detectGate | prefers critical over warning | PASS | Flag priority ordering
@ncaos/core | detection.test.ts | detectGate | MTTD measurement present | PASS | SLA baseline
@ncaos/core | detection.test.ts | detectPremise | HIGH for most unvalidated | PASS | ≥70% → HIGH/flow
@ncaos/core | detection.test.ts | detectPremise | MED for partial mismatch | PASS
@ncaos/core | detection.test.ts | detectPremise | no trigger when all validated | PASS
@ncaos/core | detection.test.ts | detectPremise | no trigger when no premises | PASS | Zero-claim guard
@ncaos/core | detection.test.ts | detectAuthority | HIGH for override attempt | PASS | scope=sys
@ncaos/core | detection.test.ts | detectAuthority | MED for legitimate downgrade | PASS
@ncaos/core | detection.test.ts | detectAuthority | no trigger when policy grants decision-ready | PASS
@ncaos/core | detection.test.ts | detectContinuity | HIGH when many tests fail | PASS
@ncaos/core | detection.test.ts | detectContinuity | MED for moderate degradation | PASS
@ncaos/core | detection.test.ts | detectContinuity | no trigger when stable | PASS
@ncaos/core | detection.test.ts | detectContinuity | always sys scope | PASS | Design invariant
@ncaos/core | scoring.test.ts | computeIntegrity | returns Available/88 for nominal | PASS
@ncaos/core | scoring.test.ts | computeIntegrity | returns Limited for low severity | PASS
@ncaos/core | scoring.test.ts | computeIntegrity | returns Limited for med severity | PASS | Boundary condition
@ncaos/core | scoring.test.ts | computeIntegrity | returns Critical for high severity | PASS
@ncaos/core | scoring.test.ts | computeIntegrity | respects CRITICAL_STRICT thresholds | PASS
@ncaos/core | scoring.test.ts | computeAuthority | returns decision-ready for nominal | PASS
@ncaos/core | scoring.test.ts | computeAuthority | returns reference-only for low severity | PASS
@ncaos/core | scoring.test.ts | computeAuthority | returns invalid for med severity | PASS
@ncaos/core | scoring.test.ts | computeAuthority | returns invalid for high severity | PASS
@ncaos/core | scoring.test.ts | computeContainmentMetrics | governedOutput < rawExposure | PASS
@ncaos/core | scoring.test.ts | computeContainmentMetrics | lower raw when integrity Available | PASS
@ncaos/core | scoring.test.ts | computeContainmentMetrics | clamps 0–100 | PASS
@ncaos/core | scoring.test.ts | scoreToContinuityState | STABLE when score ≥ stable | PASS
@ncaos/core | scoring.test.ts | scoreToContinuityState | PROVISIONAL when score ≥ provisional | PASS
@ncaos/core | scoring.test.ts | scoreToContinuityState | UNSTABLE when score < provisional | PASS
@ncaos/core | scoring.test.ts | scoreToContinuityState | uses PILOT_PROFILE thresholds | PASS
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | PASS for low blockOnContainment=false | PASS
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | DOWNGRADE for low severity | PASS
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | BLOCK for med severity | PASS
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | BLOCK for high severity | PASS
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | routing on non-PASS | PASS
@ncaos/core | verdict.test.ts | enforce ENTERPRISE_STRICT | no routing on PASS | PASS
@ncaos/core | verdict.test.ts | enforce CRITICAL_STRICT | BLOCK for all severities | PASS | Max enforcement
@ncaos/core | verdict.test.ts | enforce PILOT | PASS for low and med | PASS
@ncaos/core | verdict.test.ts | enforce PILOT | DOWNGRADE for high | PASS
@ncaos/core | verdict.test.ts | failSafeVerdict | FAIL_SAFE + invalid + score=0 | PASS | ADR-002
@ncaos/core | verdict.test.ts | validatePolicyConsistency | passes for valid policy | PASS
@ncaos/core | verdict.test.ts | validatePolicyConsistency | fails when available ≤ limited | PASS
@ncaos/core | verdict.test.ts | validatePolicyConsistency | fails when stable ≤ provisional | PASS
@ncaos/core | verdict.test.ts | loadPolicy | parses valid raw policy | PASS
@ncaos/core | verdict.test.ts | loadPolicy | throws on invalid raw input | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — lifecycle | starts and stops cleanly | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — lifecycle | returns FAIL_SAFE when not running | PASS | ADR-002
@ncaos/shell | shell-loop.test.ts | ShellLoop — lifecycle | throws on invalid policy consistency | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | returns PASS for clean input | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | sets operationalMode to NORMAL | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | sets shellIntegrity=true | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | no containment event on PASS | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | produces valid requestId | PASS | REQ-XXXXXX format
@ncaos/shell | shell-loop.test.ts | ShellLoop — clean request (PILOT) | governed output < raw exposure | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — threat (ENTERPRISE_STRICT) | returns BLOCK for high-severity | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — threat (ENTERPRISE_STRICT) | operationalMode=CONTAINMENT | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — threat (ENTERPRISE_STRICT) | emits containment event | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — threat (ENTERPRISE_STRICT) | integrity=Critical on high | PASS
@ncaos/shell | shell-loop.test.ts | ShellLoop — threat (ENTERPRISE_STRICT) | routing hint on BLOCK | PASS | SOC / Security Queue
@ncaos/shell | shell-loop.test.ts | ShellLoop — event emission | emits shell:output per process() | PASS
@ncaos/api | event-store.test.ts | EventStore — append/retrieve | appends and returns record | PASS
@ncaos/api | event-store.test.ts | EventStore — append/retrieve | null when no event | PASS
@ncaos/api | event-store.test.ts | EventStore — append/retrieve | retrieves by evidence handle | PASS
@ncaos/api | event-store.test.ts | EventStore — append/retrieve | tenant isolation on getByHandle | PASS | ADR-005
@ncaos/api | event-store.test.ts | EventStore — append/retrieve | monotonically increasing seq numbers | PASS
@ncaos/api | event-store.test.ts | EventStore — append/retrieve | independent seq numbers per tenant | PASS
@ncaos/api | event-store.test.ts | EventStore — query/pagination | returns all events for tenant | PASS
@ncaos/api | event-store.test.ts | EventStore — query/pagination | newest first | PASS
@ncaos/api | event-store.test.ts | EventStore — query/pagination | filters by layer | PASS
@ncaos/api | event-store.test.ts | EventStore — query/pagination | filters by severity | PASS
@ncaos/api | event-store.test.ts | EventStore — query/pagination | paginates with limit | PASS
@ncaos/api | event-store.test.ts | EventStore — query/pagination | cursor for second page | PASS | No overlap
@ncaos/api | event-store.test.ts | EventStore — query/pagination | empty for unknown tenant | PASS
@ncaos/api | event-store.test.ts | EventStore — stats | correct aggregate counts | PASS
@ncaos/api | event-store.test.ts | EventStore — sequence (Toru-William) | populates sequenceId from workflowId | PASS | F-02/F-03 fix
@ncaos/api | event-store.test.ts | EventStore — sequence (Toru-William) | groups events by sequenceId | PASS
@ncaos/api | event-store.test.ts | EventStore — sequence (Toru-William) | tenant isolation on sequence queries | PASS
@ncaos/api | event-store.test.ts | EventStore — sequence (Toru-William) | filters by sequenceId in query() | PASS
@ncaos/api | event-store.test.ts | EventStore — summarize (Toru-William) | null for unknown sequence | PASS
@ncaos/api | event-store.test.ts | EventStore — summarize (Toru-William) | STABLE when all PASS | PASS | consistencyScore=100
@ncaos/api | event-store.test.ts | EventStore — summarize (Toru-William) | CONTAINED when BLOCK follows DOWNGRADE | PASS | escalationDetected=True
@ncaos/api | event-store.test.ts | EventStore — summarize (Toru-William) | correct eventCount + partnerId | PASS
@ncaos/api | event-store.test.ts | EventStore — stats | activeSequences count | PASS
@ncaos/api | stores.test.ts | PolicyStore | default ENTERPRISE_STRICT for unknown tenant | PASS
@ncaos/api | stores.test.ts | PolicyStore | accepts valid policy update | PASS
@ncaos/api | stores.test.ts | PolicyStore | rejects invalid schema | PASS
@ncaos/api | stores.test.ts | PolicyStore | rejects inconsistent thresholds | PASS
@ncaos/api | stores.test.ts | PolicyStore | records policy history | PASS
@ncaos/api | stores.test.ts | PolicyStore | emits policy:changed event | PASS
@ncaos/api | stores.test.ts | PolicyStore | isolated per tenant | PASS | ADR-005
@ncaos/api | stores.test.ts | PolicyStore | resets to default | PASS
@ncaos/api | stores.test.ts | TenantDetectorRegistry | creates detector set for new tenant | PASS | ADR-005
@ncaos/api | stores.test.ts | TenantDetectorRegistry | returns same instance on subsequent calls | PASS
@ncaos/api | stores.test.ts | TenantDetectorRegistry | independent instances per tenant | PASS
@ncaos/api | stores.test.ts | TenantDetectorRegistry | resets tenant detector set | PASS
@ncaos/api | stores.test.ts | TenantDetectorRegistry | MTTD stats for all four layers | PASS
@ncaos/api | stores.test.ts | TenantDetectorRegistry | SLA healthy when no samples | PASS
@ncaos/api | stores.test.ts | TenantDetectorRegistry | tracks active tenant count | PASS
@ncaos/api | stores.test.ts | TenantDetectorRegistry | uses policy SLA values | PASS
@ncaos/api | api.test.ts | GET /v1/health | returns 200 when shell running | PASS | Phase 02 regression
@ncaos/api | api.test.ts | POST /v1/process | returns 401 without X-Partner-ID | PASS
@ncaos/api | api.test.ts | POST /v1/process | returns 400 for invalid payload | PASS
@ncaos/api | api.test.ts | POST /v1/process | returns 200 with verdict | PASS
@ncaos/api | api.test.ts | POST /v1/process | returns evidenceHandle on containment | PASS
@ncaos/api | api.test.ts | GET /v1/state | returns current GovState | PASS
@ncaos/api | api.test.ts | GET /v1/audit/:handle | returns 404 for unknown | PASS
@ncaos/api | api.test.ts | GET /v1/audit/:handle | returns event for known handle | PASS
@ncaos/api | api-v4.test.ts | GET /v1/health upgraded | slaHealthy + activeTenants fields | PASS | F-01 fix
@ncaos/api | api-v4.test.ts | GET /v1/health upgraded | 401 without X-Partner-ID | PASS
@ncaos/api | api-v4.test.ts | POST /v1/process upgraded | 200 for clean request | PASS | Per-tenant detectors
@ncaos/api | api-v4.test.ts | POST /v1/process upgraded | BLOCK + evidenceHandle for threat | PASS
@ncaos/api | api-v4.test.ts | GET /v1/audit upgraded | full EventRecord with sequenceNumber | PASS
@ncaos/api | api-v4.test.ts | GET /v1/audit upgraded | returns 404 for unknown | PASS
@ncaos/api | api-v4.test.ts | GET /v1/audit upgraded | 404 for different tenant (isolation) | PASS | ADR-005
@ncaos/api | api-v4.test.ts | GET /v1/events | returns paginated event list | PASS
@ncaos/api | api-v4.test.ts | GET /v1/events | filters by layer | PASS
@ncaos/api | api-v4.test.ts | GET /v1/events | filters by severity | PASS
@ncaos/api | api-v4.test.ts | GET /v1/events | 400 for invalid limit | PASS
@ncaos/api | api-v4.test.ts | GET /v1/events | tenant isolation enforced | PASS | ISOLATED_TENANT sees 0
@ncaos/api | api-v4.test.ts | GET /v1/events/stats | returns aggregate statistics | PASS
@ncaos/api | api-v4.test.ts | GET /v1/mttd | MTTD stats for all four layers | PASS
@ncaos/api | api-v4.test.ts | GET /v1/policy | returns active policy | PASS
@ncaos/api | api-v4.test.ts | POST /v1/policy | rejects invalid schema | PASS
@ncaos/api | api-v4.test.ts | GET /v1/policy/history | returns history array | PASS
@ncaos/api | api-v4.test.ts | GET /v1/detectors | per-tenant detector status | PASS | gateRules + mttdStats
@ncaos/detection | mttd.test.ts | MttdTracker | records sample + SLA result | PASS
@ncaos/detection | mttd.test.ts | MttdTracker | flags SLA breach | PASS | 80ms > 50ms SLA
@ncaos/detection | mttd.test.ts | MttdTracker | computes stats after samples | PASS | min/max/mean/p50
@ncaos/detection | mttd.test.ts | MttdTracker | tracks breach count | PASS
@ncaos/detection | mttd.test.ts | MttdTracker | zero stats when no samples | PASS
@ncaos/detection | mttd.test.ts | MttdTracker | resets breach count | PASS
@ncaos/detection | mttd.test.ts | DetectionRegistry | initializes all four layers | PASS
@ncaos/detection | mttd.test.ts | DetectionRegistry | uses policy SLA values | PASS
@ncaos/detection | mttd.test.ts | DetectionRegistry | healthy when no breaches | PASS
@ncaos/detection | mttd.test.ts | DetectionRegistry | throws on unknown layer | PASS
@ncaos/detection | mttd.test.ts | startTimer | positive elapsed time | PASS
@ncaos/detection | mttd.test.ts | startTimer | measures waited duration | PASS
@ncaos/detection | gate.test.ts | GateDetector — clean | no trigger on clean input | PASS | type=GATE_CLEAR
@ncaos/detection | gate.test.ts | GateDetector — clean | low severity on clean | PASS
@ncaos/detection | gate.test.ts | GateDetector — clean | MTTD ≥ 0 | PASS
@ncaos/detection | gate.test.ts | GateDetector — clean | layer=gate + detectionMode | PASS
@ncaos/detection | gate.test.ts | GateDetector — critical | HIGH for INJECTION_PATTERN | PASS | scope=sys
@ncaos/detection | gate.test.ts | GateDetector — critical | HIGH for SIGNATURE_INVALID | PASS | G-C-002
@ncaos/detection | gate.test.ts | GateDetector — critical | HIGH for KNOWN_BAD_SOURCE | PASS
@ncaos/detection | gate.test.ts | GateDetector — critical | HIGH for REPLAY_ATTACK | PASS
@ncaos/detection | gate.test.ts | GateDetector — critical | HIGH for TAMPERED_PAYLOAD | PASS
@ncaos/detection | gate.test.ts | GateDetector — critical | critical wins over warning | PASS | Priority order
@ncaos/detection | gate.test.ts | GateDetector — warning | MED for RATE_EXCEEDED | PASS | scope=req
@ncaos/detection | gate.test.ts | GateDetector — warning | MED for GEO_MISMATCH | PASS
@ncaos/detection | gate.test.ts | GateDetector — warning | MED for SCHEMA_VIOLATION | PASS | scope=flow
@ncaos/detection | gate.test.ts | GateDetector — warning | matches multiple warning rules | PASS
@ncaos/detection | gate.test.ts | GateDetector — allowlist | UNRECOGNIZED_SOURCE auto-added | PASS
@ncaos/detection | gate.test.ts | GateDetector — allowlist | no trigger for known source | PASS
@ncaos/detection | gate.test.ts | GateDetector — custom | applies custom rule | PASS | CUSTOM-001
@ncaos/detection | gate.test.ts | GateDetector — custom | returns all rules via getRules() | PASS
@ncaos/detection | detection.test.ts | PremiseDetector — clean | no trigger when all validated | PASS
@ncaos/detection | detection.test.ts | PremiseDetector — clean | PREMISE_VALIDATED type | PASS
@ncaos/detection | detection.test.ts | PremiseDetector — violations | HIGH for critical premise unvalidated | PASS | criticalViolations=1
@ncaos/detection | detection.test.ts | PremiseDetector — violations | MED for partial standard violations | PASS | 67% mismatch
@ncaos/detection | detection.test.ts | PremiseDetector — violations | unknown claim flagged | PASS | reason=unknown_claim
@ncaos/detection | detection.test.ts | PremiseDetector — violations | contract version mismatch | PASS | 1.0 vs 2.0
@ncaos/detection | detection.test.ts | PremiseDetector — violations | MTTD ≥ 0 | PASS
@ncaos/detection | detection.test.ts | AuthorityDetector — grant | decision-ready when policy allows | PASS | decision=GRANT
@ncaos/detection | detection.test.ts | AuthorityDetector — grant | no trigger reference-only granted+requested | PASS
@ncaos/detection | detection.test.ts | AuthorityDetector — downgrade | downgrades to reference-only | PASS | severity=high (F-01 fix)
@ncaos/detection | detection.test.ts | AuthorityDetector — downgrade | denies when policy grants invalid | PASS | decision=DENY
@ncaos/detection | detection.test.ts | AuthorityDetector — downgrade | chain constraint — cannot upgrade | PASS | previous=ref-only
@ncaos/detection | detection.test.ts | AuthorityDetector — override | escalation_attempt = HIGH/sys | PASS
@ncaos/detection | detection.test.ts | AuthorityDetector — override | logs every decision to audit log | PASS | 2 entries
@ncaos/detection | detection.test.ts | AuthorityDetector — override | MTTD ≥ 0 | PASS
@ncaos/detection | detection.test.ts | ContinuityDetector — stable | no trigger all tests pass | PASS | score=100
@ncaos/detection | detection.test.ts | ContinuityDetector — stable | always sys scope | PASS | Design invariant
@ncaos/detection | detection.test.ts | ContinuityDetector — stable | 12-test template | PASS
@ncaos/detection | detection.test.ts | ContinuityDetector — violations | HIGH when critical tests fail | PASS
@ncaos/detection | detection.test.ts | ContinuityDetector — violations | PROVISIONAL between thresholds | PASS
@ncaos/detection | detection.test.ts | ContinuityDetector — violations | CONTAINMENT when UNSTABLE | PASS
@ncaos/detection | detection.test.ts | ContinuityDetector — violations | OPEN→WATCHING transition | PASS
@ncaos/detection | detection.test.ts | ContinuityDetector — violations | MTTD ≥ 0 | PASS
@ncaos/detection | detection.test.ts | ContinuityDetector — violations | failRate=0.4 for 4/10 | PASS

## Manual Tests (9)
Phase 04 — Manual API Test Results (Live Server on SGWLWH000683)
Test Date: 2026-05-07 ¦ Server: http://localhost:3000 ¦ Policy: STRICT-PROD
Test | Endpoint | Method | Input | Expected | Actual Result (key fields) | Result
M-01 | /v1/health | GET | X-Partner-ID: TEST | status=OK, slaHealthy, activeTenants | status=OK ¦ watchdog=RUNNING ¦ shell=True ¦ policy=STRICT-PROD ¦ slaHealthy=True ¦ activeTenants=1 ¦ totalEvents=0 | PASS
M-02 | /v1/process | POST | sourceId=test-src-001, clean flags, all premises validated, workflowId=WF-DEMO-001 | action=PASS or DOWNGRADE, workflowId accepted | requestId=REQ-000002 ¦ action=DOWNGRADE ¦ authority=reference-only ¦ integrity=Available/88 ¦ evidenceHandle=EVD-... | PASS
M-03 | /v1/process | POST | sourceId=attacker-001, inputFlags=[INJECTION_PATTERN], 67% unvalidated, workflowId=WF-DEMO-001 | action=BLOCK, authority=invalid, integrity=Critical | requestId=REQ-000003 ¦ action=BLOCK ¦ authority=invalid ¦ integrity=Critical/29 ¦ evidenceHandle=EVD-1778168626181-5164BEB0 | PASS
M-04 | /v1/events | GET | limit=10, filter by layer=gate | records array, pagination.total ≥ 1 | records=[{EVD-1778168626181-5164BEB0, partnerId=TEST, ...}] ¦ layer=gate filter working | PASS
M-05 | /v1/events/sequence/WF-DEMO-001 | GET | workflowId=WF-DEMO-001 (4 events sent) | records grouped by workflowId | sequenceId=WF-DEMO-001 ¦ records=[EVD-...6A95ECB8, EVD-...5164BEB0, EVD-...059FA3D0, EVD-...37F0DC81] ¦ count=4 | PASS
M-05b | /v1/events/sequence/WF-DEMO-001/summary | GET | workflowId=WF-DEMO-001 | patternType, consistencyScore, escalationDetected | eventCount=4 ¦ escalationDetected=True ¦ consistencyScore=94 ¦ patternType=CONTAINED ¦ actions={DOWNGRADE,BLOCK,DOWNGRADE,BLOCK} ¦ severities={low,high,low,high} | PASS
M-06 | /v1/mttd | GET | X-Partner-ID: TEST | slaHealthy=True, 4 layers with stats | slaHealthy=True ¦ layers=[gate: sampleCount=2, slaBreach=0, slaMs=50, min≈0.53ms] | PASS
M-07 | /v1/policy | GET | X-Partner-ID: TEST | profileId=STRICT-PROD | profileId=STRICT-PROD ¦ govLevel=ENTERPRISE_STRICT ¦ blockOnContainment=True ¦ mttdSlaMs={gate:50,premise:200,authority:100,continuity:500} | PASS
M-08 | /v1/events/stats | GET | X-Partner-ID: TEST (after 4 requests) | total, byLayer, activeSequences=1 | total=4 ¦ byLayer={gate:4} ¦ bySeverity={low:2,high:2} ¦ byAction={DOWNGRADE:2,BLOCK:2} ¦ activeSequences=1 | PASS
M-09 | /v1/events + /v1/audit | GET | X-Partner-ID: OTHER_CORP | OTHER_CORP sees 0 events, 404 on handle | events: pagination.total=0 ¦ audit/EVD-...5164BEB0: 404 NOT_FOUND — isolation enforced | PASS

## Toru-William Alignment
Phase 04 — Toru-William Interface Alignment
Minimum Viable Signal Layer · Sequence-Level Behavioral Evidence · Boundary Intact
Discussion Context: After Phase 03 review, Toru and William agreed the next phase should define the "minimum viable signal layer" — the smallest interface that supports meaningful governance evidence without internal visibility.
Concept (Toru-William) | Implementation in Phase 04 | API Surface | Manual Test Evidence | Status
Minimum viable signal layer | EventRecord core fields: layer, severity, action, evidenceHandle, sequenceId, storedAt, routing, sequenceNumber — always present on every containment event | GET /v1/audit/:handle | EVD-1778168626181-5164BEB0: layer=gate, severity=high, action=BLOCK, sequenceId=WF-DEMO-001, sequenceNumber=2 | DONE
Sequence-level interpretation — moving from event-by-event to behavioral patterns | sequenceId derived from GovEvent.workflowId groups events into behavioral chains. Fixed in F-02/F-03 to carry workflowId through judge→enforcer→GovEvent→EventStore | GET /v1/events/sequence/:id | WF-DEMO-001: 4 events retrieved, both DOWNGRADE and BLOCK events grouped correctly | DONE
Consistency of enforcement across events | consistencyScore (0–100) = 100 - (action rank variance × 25). Low variance = high consistency. Score of 94 reflects mostly consistent enforcement with one escalation. | GET /v1/events/sequence/:id/summary | consistencyScore=94 for WF-DEMO-001 sequence (DOWNGRADE→BLOCK pattern, not pure chaos) | DONE
Escalation patterns — progressive severity increase | escalationDetected: true when action rank increases over time (PASS=0, DOWNGRADE=1, BLOCK=2, FAIL_SAFE=3). DOWNGRADE→BLOCK = escalation. | GET /v1/events/sequence/:id/summary | escalationDetected=True ¦ actions={DOWNGRADE,BLOCK,DOWNGRADE,BLOCK} | DONE
Stability vs deviation over time — patternType classification | 5 pattern types: STABLE (all PASS), DEGRADING (escalation without BLOCK), CONTAINED (escalation terminated by BLOCK), VOLATILE (mixed severity), UNKNOWN | GET /v1/events/sequence/:id/summary | patternType=CONTAINED — escalation detected and terminated by BLOCK, consistent with governance working as designed | DONE
Optional enrichment layer — identity/asset/session context | workflowId is the first optional enrichment field. Present when provided, absent when not. Core EventRecord fields remain mandatory regardless. | Present in EventRecord.sequenceId | activeSequences=0 when no workflowId provided; activeSequences=1 when WF-DEMO-001 provided | DONE
Boundary strictly intact — Urielle never accesses shell internals | Urielle consumes /v1/events/* endpoints only. No access to @ncaos/shell, @ncaos/detection, or @ncaos/core internals. The sequence summary is derived entirely from boundary signals. | Architecture enforced | Verified: sequence summary computed from stored EventRecords, not from live shell state | DONE
Phase 05 next step — formal AuditSignal schema | The typed contract between NCAOS boundary signals and the Urielle audit layer. Core layer (always present) + optional enrichment layers (identity, asset, session). Interface definition exercise. | To be defined Phase 05 | Not yet implemented — Phase 05 deliverable | NEXT

## Phase Status
NCAOS / EGS — Overall Phase Status (as of 2026-05-07)
Phase | Title | Week | Tests | Status | Next Action
Phase 01 | Foundation & Repo Setup — @ncaos/core | W1–2 | 47/47 | COMPLETE | Regression included in every test run
Phase 02 | Shell Engine + API Skeleton — @ncaos/shell + @ncaos/api | W2–4 | 70/70 | COMPLETE | Regression included in every test run
Phase 03 | Detection Layer — @ncaos/detection MTTD | W4–6 | 124/124 | COMPLETE | Regression included in every test run
Phase 04 | API Integration Surface — per-tenant + sequence interface | W6–8 | 181/181 | COMPLETE | Proceed to Phase 05
Phase 05 | Admin UI — React + formal AuditSignal schema (Toru-William) | W8–10 | TBD | NEXT | React Admin Terminal + typed AuditSignal contract for Urielle
Phase 06 | Hardening & Compliance — STRIDE + ISO 42001 | W10–12 | TBD | PLANNED | AI/ML threat model, pen test, MTTD SLA regression, chaos test
Phase 07 | Stakeholder Demo & Handoff — v1.0-rc | W12–14 | TBD | PLANNED | Executive demo, pilot proposal, GitHub Pages deploy
CUMULATIVE — Phases 01–04 |  |  | 181/181 | ALL PASS | Phase 05: React Admin UI + AuditSignal schema (Toru-William)