## Executive Summary
NCAOS / EGS — Phase 07 Post-Testing Report Stakeholder Demo & Handoff · Commercial Pilot Proposal · v1.0-rc Tag Demo Date: 2026-05-19 · Host: SGWLWH000683 · Phases 01–07 COMPLETE
Package | Phase | Tests | Fix | Status | Version | Notes
@ncaos/core | Phase 01 | 47 | — | PASS | v0.1.0 | No regressions
@ncaos/shell | Phase 02 | 15 | — | PASS | v0.2.0 | No regressions
@ncaos/api | Ph 02→04 | 65 | — | PASS | v0.4.0 | No regressions
@ncaos/detection | Phase 03 | 54 | — | PASS | v0.3.0 | No regressions
@ncaos/ui | Phase 05 | — | — | PASS | v0.5.0 | Manual — verified in demo
@ncaos/hardening | Phase 06 | 48 | F-01 | PASS | v0.6.0 | No regressions
egs/demo | Phase 07 | — | — | PASS | v1.0-rc | 6-step demo executed
egs/pilot | Phase 07 | — | — | DONE | v1.0-rc | 3-tier proposal delivered
ADR-008 | Phase 07 | — | — | DONE | v1.0-rc | v1.0 roadmap documented
Git tag v1.0-rc | Phase 07 | — | — | TAGGED | v1.0-rc | EGS complete — Phases 01–07
CUMULATIVE | 01–07 | 229 | — | ALL PASS | v1.0-rc | 229 automated + 6-step live demo
PHASE 07 — NEW DELIVERABLES
File | Purpose | Demo Step | Audience | Status | ADR
egs/demo/demo-scenario.ts | 6-step live containment demo script — D-01→D-06 | D-01/06 | All | PASS | —
egs/pilot/pilot-proposal.ts | 3-tier commercial pilot structure (Observe/Contain/Audit) | — | Executive/Legal | DONE | —
docs/adr/ADR-008-v1-roadmap.md | v1.0-rc scope, 4 deferred items, production readiness criteria | — | Architect | DONE | ADR-008
Git tag v1.0-rc | Marks EGS as complete — Phases 01–07 — demo ready | — | All | TAGGED | —
KEY FIX: WebSocket I-01 RESOLVED in Phase 07 Build
Phase 05 I-01 (socket.send TypeError in @fastify/websocket): RESOLVED in Phase 07 production build. Running log confirms [WS] Client connected: GLOBAL_ENT_2026 / [WS] Client disconnected: GLOBAL_ENT_2026 — WebSocket live push fully operational during demo. Admin Terminal connects on all 4 role tabs.
TORU-WILLIAM ALIGNMENT — D-04 Sequence Summary (Live Demo)
Field | Observed Value | Significance
sequenceId | WF-DEMO-LIVE-001 | Workflow correctly grouped across 2 events
patternType | CONTAINED | Escalation detected and terminated at boundary
escalationDetected | True | DOWNGRADE→BLOCK pattern documented
consistencyScore | 94 | Enforcement was consistent (0–100 scale)
eventCount | 2 | Full chain visible: DOWNGRADE event + BLOCK event
layers | {gate, authority} | Multi-layer detection captured
severities | {low, high} | Severity escalation documented
actions | {DOWNGRADE, BLOCK} | Complete action chain for audit trail
NCAOS-Urielle · github.com/wholidi/NCAOS-Urielle ¦ Non-Public / Concept Artifact ¦ v1.0-rc ¦ EGS COMPLETE

## Demo Execution Log
NCAOS / EGS — Phase 07 ¦ Stakeholder Demo Execution Log ¦ 2026-05-19 ¦ DEMO_ENT_2026 tenant
Step | Check / Action | Expected | Observed | Result
D-01 Health Baseline (All stakeholders) | GET /v1/health — status, watchdog, slaHealthy, policy | status=OK, watchdog=RUNNING, slaHealthy=True, policy=STRICT-PROD | status=OK · watchdog=RUNNING · shell=True · policy=STRICT-PROD · slaHealthy=True · activeTenants=1 · totalEvents=0 | PASS
D-01 Health Baseline | Governance narrative point: EGS online, boundary protected, no model weight access | Shell operational, ADR-002 FAIL_SAFE enabled | failSafeEnabled confirmed in /v1/state output. ShellLoop Started — policy: STRICT-PROD in server log. | PASS
D-02 Clean Request (Executive, Architect) | POST /v1/process — sourceId=enterprise-svc-001, all premises validated, workflowId=WF-DEMO-LIVE-001 | action=PASS or DOWNGRADE, authority=decision-ready or reference-only | REQ-000002 · action=DOWNGRADE · authority=reference-only · integrity={level=Available, score=88} · evidenceHandle=EVD-1779183741527-EEFE2F6F · processingMs=0 | PASS
D-03 Threat → BLOCK (Executive, Architect) | POST /v1/process — INJECTION_PATTERN + SIGNATURE_INVALID flags, overrideAttempted=$false, workflowId=WF-DEMO-LIVE-001 | action=BLOCK, authority=invalid, integrity=Critical, evidenceHandle captured | REQ-000003 · action=BLOCK · authority=invalid · integrity={level=Critical, score=29} · evidenceHandle=EVD-1779184017201-38BE649C · processingMs=0 | PASS
D-03 Threat → BLOCK | Evidence handle captured for D-05 audit retrieval | evidenceHandle string returned, non-null | $handle = $result.evidenceHandle confirmed = EVD-1779185789352-BF52C998 (second session) | PASS
D-04 Sequence Summary (Toru alignment) | GET /v1/events/sequence/WF-DEMO-LIVE-001/summary | patternType=CONTAINED, escalationDetected=True, consistencyScore≥80, eventCount≥2 | sequenceId=WF-DEMO-LIVE-001 · patternType=CONTAINED · escalationDetected=True · consistencyScore=94 · eventCount=2 · firstDetectedAt=5/19/2026 10:16:16 · layers={gate,authority} · actions={DOWNGRADE,BLOCK} | PASS
D-04 Sequence Summary | Note: first run returned NOT_FOUND (server restart lost in-memory events). Re-generated events in second session. | Reproducible after restart with fresh events | Second session (WF-DEMO-LIVE-001): sequence summary 200 OK. EventStore is in-memory — expected to reset on restart. Phase 07 ADR-008 notes TimescaleDB persistence as SHOULD. | PASS
D-05 Audit Trail (Legal/Compliance) | GET /v1/audit/EVD-1779185776973-8D24C988 — full EventRecord retrieval | evidenceHandle, event.layer, event.severity, event.detectionMode, event.routing, mttdMs, sequenceNumber | evidenceHandle=EVD-1779185776973-8D24C988 · event.layer=gate · event.scope=req · event.severity=low · event.detectionMode=Real-time Gate Enforcement · integrity={level=Available,score=88} · routing={hint=SOC/Security Queue} · mttdMs=1 · storedAt=2026-05-19T10:16:16.976Z · sequenceNumber=1 | PASS
D-05 Audit Trail | GET /v1/audit/EVD-1779185789352-BF52C998 — BLOCK event full record | event.type=AUTHORITY_REVOKED, event.severity=high, event.layer=authority | event.type=AUTHORITY_REVOKED · event.layer=authority · event.scope=sys · event.severity=high · event.detectionMode=Authority Boundary Enforcement · integrity={level=Critical,score=29} · authority={authority=invalid,score=22} · routing={hint=Governance/Policy Review} · sequenceNumber=2 | PASS
D-06 GovState (Executive) | GET /v1/state — operationalMode, rawExposurePct, governedOutputPct, activeEvent | operationalMode=CONTAINMENT, rawExposurePct=100, governedOutputPct<100 | systemStatus=ENFORCING(STRICT) · operationalMode=CONTAINMENT · shellIntegrity=True · integrity={level=Critical,score=29} · rawExposurePct=100 · governedOutputPct=54 · coreIsolationPct=35 · contextDriftPressurePct=43 · latencyOverheadMs=369 · activeEvent=AUTHORITY_REVOKED/HIGH · lastRouting=Governance/Policy Review · equivalenceTests={passed=12,total=12} | PASS
Admin Terminal (All roles) | http://localhost:5173 — [SOC OPERATOR] BLOCK/DOWNGRADE events, MTTD panel | BLOCK events in red, DOWNGRADE in amber, EVD handles visible with ↗ indicator | Admin Terminal loads. WebSocket [WS] Client connected: GLOBAL_ENT_2026 confirmed in server log. SOC view shows events. Filter ?layer=gate confirmed in API log. | PASS
Admin Terminal | [AUDITOR] — Sequence panel loads from evidence handle click | patternType=CONTAINED visible, escalationDetected=True, consistencyScore shown | /v1/events/sequence/WF-DEMO-LIVE-001/summary confirmed 200 OK in server log. Sequence panel displayed in UI. | PASS
Admin Terminal | [EXECUTIVE] — trend chart shows integrity drop on BLOCK event | RAW_EXPOSURE vs GOVERNED_OUTPUT bars, trend line visible | Executive view loaded. /v1/state polled. Trend visible (LineChart renders from /v1/events). | PASS
Git Commit + Tag | git commit 'feat: Phase 07 complete — stakeholder demo + v1.0-rc' | Commit to main succeeds | Committed. egs/demo/ + egs/pilot/ + ADR-008 staged. | PASS
Git Commit + Tag | git tag -a v1.0-rc + git push origin v1.0-rc | Tag pushed to origin, visible under GitHub Releases | v1.0-rc tagged and pushed. GitHub release created with Phase 01–07 summary. | PASS

## v1.0 Production Roadmap
NCAOS / EGS — Phase 07 ¦ v1.0 Production Roadmap ¦ ADR-008 · docs/adr/ADR-008-v1-roadmap.md
Priority | Item | Category | Effort | STRIDE Ref | Notes
MUST | WebSocket authentication in upgrade handler | Security | 1 day | S-003 | I-01 now resolved in production; auth layer still needed
MUST | Stack trace stripping in production error responses | Security | 0.5 day | I-001 | Dev mode shows structured errors
MUST | HMAC-signed evidence handles | Security | 1 day | R-001 | Handle integrity for legal admissibility
MUST | String sanitization in ProcessRequestSchema | Security | 0.5 day | T-003 | sourceId + inputFlags fields
MUST | activatedBy bound to JWT sub in PolicyStore | Security | 0.5 day | R-002 | Policy audit trail identity binding
MUST | /v1/mttd restricted to admin role JWT claim | Security | 0.5 day | I-003 | Performance data access control
SHOULD | TimescaleDB persistence for EventStore | Infrastructure | 3 days | — | Events survive restart — Phase 07 demo required restart workaround
SHOULD | Redis-backed TenantDetectorRegistry (multi-node) | Infrastructure | 2 days | — | Horizontal scaling for enterprise deployment
SHOULD | RS256 JWT key rotation (replace HS256) | Security | 1 day | — | Production-grade key management
SHOULD | GitHub Pages demo deployment | Demo | 1 day | — | Shareable demo URL for prospects
NICE | HMAC-signed sourceId for Gate allowlist verification | Security | 2 days | S-002 | PT-002 noted item
NICE | Per-tenant event ingestion rate limit (EventStore) | Security | 1 day | D-002 | PT not yet executed
NICE | Automated ISO 42001 evidence package generation | Compliance | 3 days | — | Urielle integration Phase 1

## Commercial Pilot Tiers
NCAOS / EGS — Phase 07 ¦ Commercial Pilot Proposal · egs/pilot/pilot-proposal.ts
TIER 1 — OBSERVE (4 WEEKS)
Scope | Deliverables | Success Criteria
EGS in PILOT-OBS mode (no blocking) | MTTD baseline report over 4 weeks | All requests within MTTD SLA (p99 per policy)
Single AI/OS boundary endpoint instrumented | Event log analysis — frequency and pattern | Zero false positives blocking legitimate requests
Read access to /v1/events, /v1/mttd, /v1/state | GovState trend — RAW vs GOVERNED comparison | Evidence handles structured for compliance review
Admin Terminal for architecture team | Phase 01 AuditSignal samples for Urielle review | Architecture team confirms no model access
TIER 2 — CONTAIN (8 WEEKS)
Scope | Deliverables | Success Criteria
EGS in ENTERPRISE_STRICT mode (DOWNGRADE + BLOCK active) | STRIDE threat model for enterprise AI/OS landscape | Containment events reflect genuine governance violations
Custom gate rules for enterprise threat patterns | ISO 42001 control mapping with evidence | False positive rate < 0.5%
Policy profile tuned by enterprise team | Pen test results for enterprise attack vectors | Compliance confirms evidence trail meets audit requirements
Per-tenant isolation validated | AuditSignal samples for compliance/legal review | No FAIL_SAFE activations over 8 weeks
TIER 3 — AUDIT (12 WEEKS)
Scope | Deliverables | Success Criteria
Full Urielle audit layer integration — AuditSignal consumption | ISO 42001 compliance evidence for Clause 8 and 9 | Legal/compliance signs off on evidence trail quality
ISO 42001 formal audit trail generation | Formal audit findings report (Urielle/MLP) | ISO 42001 8.4, 9.1, 9.2 IMPLEMENTED accepted
Multi-tenant deployment (up to 5 business units) | v1.0-rc deployment guide for enterprise infrastructure | Architecture confirms no internal visibility required
JWT + RBAC rolled out to all API consumers | Phase 07 hardening actions completed | Commercial terms agreed for v1.0 production

## Regression Summary (229)
NCAOS / EGS — Phase 07 ¦ Phase 01–06 Regression Check ¦ 229 Automated Tests — ALL PASS ¦ 2026-05-19
Package | Phase | Test Files | Tests | Duration | Status
@ncaos/core | Phase 01 | 3 (scoring, detection, verdict) | 47 | ~2s | PASS
@ncaos/shell | Phase 02 | 1 (shell-loop) | 15 | ~1s | PASS
@ncaos/api | Ph 02→04 | 4 (event-store, stores, api, api-v4) | 65 | ~10s | PASS
@ncaos/detection | Phase 03 | 3 (gate, detection, mttd) | 54 | ~1s | PASS
@ncaos/ui | Phase 05 | — (no automated test script) | — | — | PASS
@ncaos/hardening | Phase 06 | 5 (stride, auth, chaos, iso42001, mttd-r) | 48 | ~3s | PASS
CUMULATIVE | 01–06 | 16 files | 229 | ~17s | ALL PASS
Production build confirmed: npm.cmd run build --workspaces completed successfully on SGWLWH000683. @ncaos/ui Vite production build: 878 modules, dist/assets/index-BjNu-vPh.js 592.57 kB. No build errors. API dist/server.js deployed for demo.